## Employees
Employee ID | Person Name | Role | Department
EMP001 | Ana Markovic Smith | Senior Clinical Research Associate | Clinical Operations
EMP002 | Marko Petrovic | Clinical Research Associate | Clinical Operations
EMP003 | Jelena Nikolic | Clinical Trial Assistant | Clinical Operations
EMP004 | Stefan Ilic | Data Manager | Data Management

## Courses
Course ID | Training Name | Category | Required? | Validity Months
CRS001 | GCP Training | GCP | Yes | 24
CRS002 | Protocol Training | Protocol | Yes | 12
CRS003 | TMF Training | TMF | Yes | 12
CRS004 | EDC System Training | Systems | Yes | 12
CRS005 | Safety Reporting Training | Safety | Yes | 12
CRS006 | ICH Guidelines Refresher | GCP | No | 24
CRS007 | Investigator Meeting Training | Protocol | Yes | 12
CRS008 | Data Privacy Training | Compliance | Yes | 24

## Training Tracker
Study ID | Employee ID | CourseID | Person Name | Role | Training Name | Training Hours | Required / Optional | Assigned Date | Due Date | Completed Date | Status | Started? | Days Overdue | Hourly Rate | Non Compliance Cost | Notes
ABC-001 | EMP001 | CRS001 | Ana Markovic Smith | Senior Clinical Research Associate | GCP Training | 4 | Yes | 2026-08-01 | 2026-08-08 | 2026-08-06 | Completed | Yes | 0
ABC-001 | EMP002 | CRS002 | Marko Petrovic | Clinical Research Associate | Protocol Training | 3 | Yes | 2026-08-02 | 2026-08-09 |  | Overdue | Yes | 57
ABC-001 | EMP003 | CRS003 | Jelena Nikolic | Clinical Trial Assistant | TMF Training | 2 | Yes | 2026-08-03 | 2026-08-10 | 2026-08-10 | Completed | Yes | 0
ABC-001 | EMP004 | CRS004 | Stefan Ilic | Data Manager | EDC System Training | 3 | Yes | 2026-08-04 | 2026-08-11 |  | Overdue | Yes | 55
ABC-001 | EMP001 | CRS005 | Ana Markovic Smith | Senior Clinical Research Associate | Safety Reporting Training | 4 | Yes | 2026-08-05 | 2026-08-12 | 2026-08-13 | Completed | Yes | 1
ABC-001 | EMP003 | CRS006 | Jelena Nikolic | Clinical Trial Assistant | ICH Guidelines Refresher | 2 | No | 2026-08-06 | 2026-08-20 |  | Overdue | Yes | 46
ABC-001 | EMP002 | CRS007 | Marko Petrovic | Clinical Research Associate | Investigator Meeting Training | 5 | Yes | 2026-08-07 | 2026-08-14 | 2026-08-14 | Completed | Yes | 0
ABC-001 | EMP004 | CRS008 | Stefan Ilic | Data Manager | Data Privacy Training | 2 | Yes | 2026-08-08 | 2026-08-15 |  | Overdue | Yes | 51
Formulas:
Status = IF([Completed Date]<>"","Completed",IF([Due Date]<TODAY(),"Overdue",IF([Started?]="Yes","In Progress","Not Started")))
Days Overdue = IF(Training_Tracker[[#This Row],[Status]]="Completed",MAX(0,Training_Tracker[[#This Row],[Completed Date]]-Training_Tracker[[#This Row],[Due Date]]),MAX(0,TODAY()-Training_Tracker[[#This Row],[Due Date]]))

## TMF Document Tracker
Study ID | Document ID | TMF Zone | Artifact | Document Name | Version | Document Status | Owner | Date Received | Due Date | QC Status | Notes | System Status | Days Overdue | Overall Check
ST-001 | DOC-001 | Trial Management | 1 | Study Plan | 1 | Approved | Ana Markovic Smith | 2026-08-01 | 2026-08-05 | Passed | Final approved version | Completed | 0 | PASS
ST-001 | DOC-002 | Trial Management | 2 | Protocol | 2 | Approved | Marko Petrovic | 2026-08-03 | 2026-08-07 | Passed | Current protocol version | Completed | 0 | PASS
ST-001 | DOC-003 | Regulatory | 1 | Regulatory Approval | 1 | Pending QC | Jelena Nikolic | 2026-08-08 | 2026-08-12 | In Review | QC review pending | Overdue | 54 | FAIL
ST-001 | DOC-004 | Safety | 1 | Safety Management Plan | 1 | Approved | Stefan Ilic | 2026-08-05 | 2026-08-10 | Passed | No issues identified | Completed | 0 | PASS
ST-002 | DOC-005 | Trial Management | 3 | Monitoring Plan | 1 | Draft | Ana Markovic Smith | 2026-08-15 | 2026-08-22 | Not Started | Awaiting final review | Overdue | 44 | FAIL
ST-002 | DOC-006 | Site Management | 1 | Site Initiation Report | 1 | Approved | Marko Petrovic | 2026-08-18 | 2026-08-20 | Passed | Filed after site initiation | Completed | 0 | PASS
ST-002 | DOC-007 | Data Management | 2 | Data Management Plan | 1.1 | Pending QC | Stefan Ilic | 2026-08-20 | 2026-08-25 | Failed | Missing QC evidence | Overdue | 41 | FAIL
ST-002 | DOC-008 | Regulatory | 2 | Ethics Committee Submission | 1 | Overdue | Jelena Nikolic | 2026-08-20 | 2026-08-28 | Not Started | Submission package incomplete | Overdue | 38 | FAIL
Formulas:
System Status = IF([Document Status]="Approved","Completed",IF([Due Date]<TODAY(),"Overdue", IF([Document Status]="Pending QC","In Progress","Not Started")))
Days Overdue = IF([System Status]="Overdue",MAX(0,TODAY()-[Due Date]),0)

## Issue Log
Issue ID | Study ID | Issue Date | Issue Category | Description | Priority | Owner | Status | Due Date | Resolution Date | Days Open | Notes | Overdue?
ISS-001 | ST-001 | 2026-08-03 | System Access | CRA unable to access EDC system | High | Ana Markovic Smith | Open | 2026-08-05 |  | 63 | Access request submitted | Overdue
ISS-002 | ST-001 | 2026-08-05 | Data Discrepancy | Missing subject visit data identified in EDC | Medium | Stefan Ilic | In Progress | 2026-08-10 |  | 61 | Data review in progress | Overdue
ISS-003 | ST-001 | 2026-08-08 | TMF | Missing essential document in TMF | High | Jelena Nikolic | Open | 2026-08-12 |  | 58 | Document requested from site | Overdue
ISS-004 | ST-001 | 2026-08-10 | Training | Required GCP training not completed | High | Marko Petrovic | Resolved | 2026-08-11 | 2026-08-11 | 1 | Training completed | On Track
ISS-005 | ST-002 | 2026-08-15 | QC | Incorrect document version identified | Medium | Jelena Nikolic | In Progress | 2026-08-20 |  | 51 | Correct version requested | Overdue
ISS-006 | ST-002 | 2026-08-18 | System Issue | EDC page not loading for site user | Critical | Stefan Ilic | Open | 2026-08-19 |  | 48 | Technical investigation required | Overdue
ISS-007 | ST-002 | 2026-08-22 | Submission | Late regulatory submission package | High | Jelena Nikolic | Resolved | 2026-08-25 | 2026-08-24 | 2 | Submission completed | On Track
ISS-008 | ST-002 | 2026-08-25 | Data Quality | Inconsistent subject data detected during review | Medium | Stefan Ilic | Open | 2026-08-30 |  | 41 | Requires data verification | Overdue
Formulas:
Days Open = IF([Status]="Resolved", [Resolution Date]-[Issue Date],TODAY()-[Issue Date])
Overdue? = IF(AND([Status]<>"Resolved",[Due Date]<TODAY()),"Overdue","On Track")

## Deliverables and Milestones
Study ID | Deliverable ID | Deliverable Type | Deliverable Name | Owner | Planned Date | Due Date | Completion Date | Status | Priority | Days Overdue | Overall Check | Notes
ST-001 | DEL-001 | Study Document | Final Study Protocol | Ana Markovic Smith | 2026-08-01 | 2026-08-05 | 2026-08-05 | Completed | High | 0 | PASS | Final approved protocol
ST-001 | DEL-002 | Regulatory | Regulatory Submission Package | Jelena Nikolic | 2026-08-03 | 2026-08-10 |  | Overdue | Critical | 56 | FAIL | Submission package incomplete
ST-001 | DEL-003 | TMF | TMF Filing Package | Marko Petrovic | 2026-08-05 | 2026-08-12 |  | In Progress | High | 54 | PASS | Filing in progress
ST-001 | DEL-004 | Data | Database Review Report | Stefan Ilic | 2026-08-08 | 2026-08-15 | 2026-08-15 | Completed | Medium | 0 | PASS | Database review completed
ST-002 | DEL-005 | Study Document | Monitoring Plan | Ana Markovic Smith | 2026-08-15 | 2026-08-22 |  | Draft | High | 44 | PASS | Awaiting final review
ST-002 | DEL-006 | Site Management | Site Initiation Report | Marko Petrovic | 2026-08-18 | 2026-08-20 | 2026-08-20 | Completed | Medium | 0 | PASS | Site initiation completed
ST-002 | DEL-007 | Data | Data Management Plan | Stefan Ilic | 2026-08-20 | 2026-08-25 |  | In Progress | High | 41 | PASS | Data management review ongoing
ST-002 | DEL-008 | Regulatory | Ethics Committee Submission | Jelena Nikolic | 2026-08-20 | 2026-08-28 |  | Overdue | Critical | 38 | FAIL | Submission delayed
Formulas:
Days Overdue = IF([Status]="Completed", MAX(0,[Completion Date]-[Due Date]),MAX(0,TODAY()-[Due Date]))

## Data Quality
Check | Result
Invalid Employee IDs | 0
Invalid Course IDs | 0
Missing Due Dates | 0
Invalid Date Sequence | 0
Overall FAIL Records | 0
Overall PASS Records | 8
Overall Data Quality | PASS
Row | Employee ID | Employee Check | Course ID | Course Check | Due Date Check | Date Sequence Check | Completion Check | Overall Check
2 | EMP001 | Valid | CRS001 | Valid | Valid | Valid | Valid | PASS
3 | EMP002 | Valid | CRS002 | Valid | Valid | Valid | N/A | PASS
4 | EMP003 | Valid | CRS003 | Valid | Valid | Valid | Valid | PASS
5 | EMP004 | Valid | CRS004 | Valid | Valid | Valid | N/A | PASS
6 | EMP001 | Valid | CRS005 | Valid | Valid | Valid | Valid | PASS
7 | EMP003 | Valid | CRS006 | Valid | Valid | Valid | N/A | PASS
8 | EMP002 | Valid | CRS007 | Valid | Valid | Valid | Valid | PASS
9 | EMP004 | Valid | CRS008 | Valid | Valid | Valid | N/A | PASS

## TMF Data Quality
Check | Result
Missing Document ID | 0
Missing Document Name | 0
Missing Due Date | 0
Invalid Date Sequence | 0
QC Failed | 1
Overall FAIL Records | 4

## Training KPIs
KPI | Value
Total Training Hours | 25
Completed Training Hours | 15
Required Training Hours | 23
Overdue Training Hours | 10
Completed Required Training Hours | 15
Overdue Required Training Hours | 8
Completed Training Records | 4
Overdue Training Records | 3

## TMF KPIs
KPI | Result
Total Documents | 8
Approved Documents | 4
Overdue Documents | 1
Pending QC Documents | 2
QC Failed Documents | 1
Completed Documents | 4
Documents in Progress | 0
Documents Not Started | 0

## Issue KPIs
KPI | Result
Total Issues | 8
Open Issues | 4
In Progress Issues | 2
Resolved Issues | 2
Critical Issues | 1
High Priority Issues | 4
Overdue Issues | 6

## Deliverables KPIs
KPI | Result
Total Deliverables | 8
Completed Deliverables | 3
Overdue Deliverables | 2
In Progress Deliverables | 2
Draft Deliverables | 0
Critical Deliverables | 2
High Priority Deliverables | 4
Failed Deliverables | 2

## Training Pivot - Emp Status (hidden)
Count of Training Name | Column Labels
Row Labels | Completed | Overdue | Grand Total
Ana Markovic Smith | 2 |  | 2
Jelena Nikolic | 1 | 1 | 2
Marko Petrovic | 1 | 1 | 2
Stefan Ilic |  | 2 | 2
Grand Total | 4 | 4 | 8
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Training Pivot - Role (hidden)
Count of Training Name | Column Labels
Row Labels | Completed | Overdue | Grand Total
Clinical Research Associate | 1 | 1 | 2
Clinical Trial Assistant | 1 | 1 | 2
Data Manager |  | 2 | 2
Senior Clinical Research Associate | 2 |  | 2
Grand Total | 4 | 4 | 8

## Training Pivot - Course Status (hidden)
Count of Training Name | Column Labels
Row Labels | Completed | Overdue | Grand Total
Data Privacy Training |  | 1 | 1
EDC System Training |  | 1 | 1
GCP Training | 1 |  | 1
ICH Guidelines Refresher |  | 1 | 1
Investigator Meeting Training | 1 |  | 1
Protocol Training |  | 1 | 1
Safety Reporting Training | 1 |  | 1
TMF Training | 1 |  | 1
Grand Total | 4 | 4 | 8

## Training Pivot - Hours (hidden)
Sum of Training Hours | Column Labels
Row Labels | Completed | Overdue | Grand Total
Ana Markovic Smith | 8 |  | 8
Jelena Nikolic | 2 | 2 | 4
Marko Petrovic | 5 | 3 | 8
Stefan Ilic |  | 5 | 5
Grand Total | 15 | 10 | 25

## TMF Pivot Status (hidden)
Count of Document ID | Column Labels
Row Labels | Data Management | Regulatory | Safety | Site Management | Trial Management | Grand Total
Approved |  |  | 1 | 1 | 2 | 4
Draft |  |  |  |  | 1 | 1
Overdue |  | 1 |  |  |  | 1
Pending QC | 1 | 1 |  |  |  | 2
Grand Total | 1 | 2 | 1 | 1 | 3 | 8

## Training Dashboard
Clinical Training Compliance Dashboard
Total Training Hours | Completed Training Hours | Required Training Hours | Overdue Training Hours | Completed Training Records | Overdue Training Records
25 | 15 | 23 | 10 | 4 | 3

## TMF Document Control Dashboard
KPI | Result
Total Documents | 8
Approved Documents | 4
Overdue Documents | 1
Pending QC Documents | 2
QC Failed Documents | 1
Completed Documents | 4

## PQ_Training_Output
Study ID | Employee ID | CourseID | Training Hours | Required / Optional | Assigned Date | Due Date | Completed Date | Status | Started? | Days Overdue | Hourly Rate | Non Compliance Cost | Notes | Person Name | Role | Department | Training Name | Category | Required? | Validity Months | Employee ID Check | Course ID Check | Completion Date Check | Overall Check | Overdue?
ABC-001 | EMP001 | CRS001 | 4 | Yes | 2026-08-01 | 2026-08-08 | 2026-08-06 | Completed | Yes | 0 |  |  |  | Ana Markovic Smith | Senior Clinical Research Associate | Clinical Operations | GCP Training | GCP | Yes | 24 | Valid | Valid | Valid | PASS | Not Overdue
ABC-001 | EMP001 | CRS005 | 4 | Yes | 2026-08-05 | 2026-08-12 | 2026-08-13 | Completed | Yes | 1 |  |  |  | Ana Markovic Smith | Senior Clinical Research Associate | Clinical Operations | Safety Reporting Training | Safety | Yes | 12 | Valid | Valid | Valid | PASS | Not Overdue
ABC-001 | EMP002 | CRS002 | 3 | Yes | 2026-08-02 | 2026-08-09 |  | Overdue | Yes | 57 |  |  |  | Marko Petrovic | Clinical Research Associate | Clinical Operations | Protocol Training | Protocol | Yes | 12 | Valid | Valid | Valid | PASS | Overdue
ABC-001 | EMP003 | CRS003 | 2 | Yes | 2026-08-03 | 2026-08-10 | 2026-08-10 | Completed | Yes | 0 |  |  |  | Jelena Nikolic | Clinical Trial Assistant | Clinical Operations | TMF Training | TMF | Yes | 12 | Valid | Valid | Valid | PASS | Not Overdue
ABC-001 | EMP004 | CRS004 | 3 | Yes | 2026-08-04 | 2026-08-11 |  | Overdue | Yes | 55 |  |  |  | Stefan Ilic | Data Manager | Data Management | EDC System Training | Systems | Yes | 12 | Valid | Valid | Valid | PASS | Overdue
ABC-001 | EMP003 | CRS006 | 2 | No | 2026-08-06 | 2026-08-20 |  | Overdue | Yes | 46 |  |  |  | Jelena Nikolic | Clinical Trial Assistant | Clinical Operations | ICH Guidelines Refresher | GCP | No | 24 | Valid | Valid | Valid | PASS | Overdue
ABC-001 | EMP002 | CRS007 | 5 | Yes | 2026-08-07 | 2026-08-14 | 2026-08-14 | Completed | Yes | 0 |  |  |  | Marko Petrovic | Clinical Research Associate | Clinical Operations | Investigator Meeting Training | Protocol | Yes | 12 | Valid | Valid | Valid | PASS | Not Overdue
ABC-001 | EMP004 | CRS008 | 2 | Yes | 2026-08-08 | 2026-08-15 |  | Overdue | Yes | 51 |  |  |  | Stefan Ilic | Data Manager | Data Management | Data Privacy Training | Compliance | Yes | 24 | Valid | Valid | Valid | PASS | Overdue

## PQ_Employees_Output
Employee ID | Person Name | Role | Department
EMP001 | Ana Markovic Smith | Senior Clinical Research Associate | Clinical Operations
EMP002 | Marko Petrovic | Clinical Research Associate | Clinical Operations
EMP003 | Jelena Nikolic | Clinical Trial Assistant | Clinical Operations
EMP004 | Stefan Ilic | Data Manager | Data Management

## PQ_Courses_Output
Course ID | Training Name | Category | Required? | Validity Months
CRS001 | GCP Training | GCP | Yes | 24
CRS002 | Protocol Training | Protocol | Yes | 12
CRS003 | TMF Training | TMF | Yes | 12
CRS004 | EDC System Training | Systems | Yes | 12
CRS005 | Safety Reporting Training | Safety | Yes | 12
CRS006 | ICH Guidelines Refresher | GCP | No | 24
CRS007 | Investigator Meeting Training | Protocol | Yes | 12
CRS008 | Data Privacy Training | Compliance | Yes | 24

## PQ_TMF_Output
Study ID | Document ID | TMF Zone | Artifact | Document Name | Version | Document Status | Owner | Date Received | Due Date | QC Status | Notes | System Status | Days Overdue | Overall Check | Document ID Check | Due Date Check | QC Check
ST-001 | DOC-001 | Trial Management | 1 | Study Plan | 1 | Approved | Ana Markovic Smith | 2026-08-01 | 2026-08-05 | Passed | Final approved version | Completed | 0 | PASS | Valid | Valid | Valid
ST-001 | DOC-002 | Trial Management | 2 | Protocol | 2 | Approved | Marko Petrovic | 2026-08-03 | 2026-08-07 | Passed | Current protocol version | Completed | 0 | PASS | Valid | Valid | Valid
ST-001 | DOC-003 | Regulatory | 1 | Regulatory Approval | 1 | Pending QC | Jelena Nikolic | 2026-08-08 | 2026-08-12 | In Review | QC review pending | Overdue | 54 | FAIL | Valid | Valid | Valid
ST-001 | DOC-004 | Safety | 1 | Safety Management Plan | 1 | Approved | Stefan Ilic | 2026-08-05 | 2026-08-10 | Passed | No issues identified | Completed | 0 | PASS | Valid | Valid | Valid
ST-002 | DOC-005 | Trial Management | 3 | Monitoring Plan | 1 | Draft | Ana Markovic Smith | 2026-08-15 | 2026-08-22 | Not Started | Awaiting final review | Overdue | 44 | FAIL | Valid | Valid | Valid
ST-002 | DOC-006 | Site Management | 1 | Site Initiation Report | 1 | Approved | Marko Petrovic | 2026-08-18 | 2026-08-20 | Passed | Filed after site initiation | Completed | 0 | PASS | Valid | Valid | Valid
ST-002 | DOC-007 | Data Management | 2 | Data Management Plan | 1.1 | Pending QC | Stefan Ilic | 2026-08-20 | 2026-08-25 | Failed | Missing QC evidence | Overdue | 41 | FAIL | Valid | Valid | QC Failed
ST-002 | DOC-008 | Regulatory | 2 | Ethics Committee Submission | 1 | Overdue | Jelena Nikolic | 2026-08-20 | 2026-08-28 | Not Started | Submission package incomplete | Overdue | 38 | FAIL | Valid | Valid | Valid

## PQ_Issue_Output
Issue ID | Study ID | Issue Date | Issue Category | Description | Priority | Owner | Status | Due Date | Resolution Date | Days Open | Notes | Overdue? | Issue ID Check | Due Date Check | Overall Check PQ
ISS-001 | ST-001 | 2026-08-03 | System Access | CRA unable to access EDC system | High | Ana Markovic Smith | Open | 2026-08-05 |  | 63 | Access request submitted | Overdue | Valid | Valid | PASS
ISS-002 | ST-001 | 2026-08-05 | Data Discrepancy | Missing subject visit data identified in EDC | Medium | Stefan Ilic | In Progress | 2026-08-10 |  | 61 | Data review in progress | Overdue | Valid | Valid | PASS
ISS-003 | ST-001 | 2026-08-08 | TMF | Missing essential document in TMF | High | Jelena Nikolic | Open | 2026-08-12 |  | 58 | Document requested from site | Overdue | Valid | Valid | PASS
ISS-004 | ST-001 | 2026-08-10 | Training | Required GCP training not completed | High | Marko Petrovic | Resolved | 2026-08-11 | 2026-08-11 | 1 | Training completed | On Track | Valid | Valid | PASS
ISS-005 | ST-002 | 2026-08-15 | QC | Incorrect document version identified | Medium | Jelena Nikolic | In Progress | 2026-08-20 |  | 51 | Correct version requested | Overdue | Valid | Valid | PASS
ISS-006 | ST-002 | 2026-08-18 | System Issue | EDC page not loading for site user | Critical | Stefan Ilic | Open | 2026-08-19 |  | 48 | Technical investigation required | Overdue | Valid | Valid | PASS
ISS-007 | ST-002 | 2026-08-22 | Submission | Late regulatory submission package | High | Jelena Nikolic | Resolved | 2026-08-25 | 2026-08-24 | 2 | Submission completed | On Track | Valid | Valid | PASS
ISS-008 | ST-002 | 2026-08-25 | Data Quality | Inconsistent subject data detected during review | Medium | Stefan Ilic | Open | 2026-08-30 |  | 41 | Requires data verification | Overdue | Valid | Valid | PASS

## PQ_Deliverables_Output
Study ID | Deliverable ID | Deliverable Type | Deliverable Name | Owner | Planned Date | Due Date | Completion Date | Status | Priority | Days Overdue | Overall Check | Notes | Deliverable ID Check | Due Date Check | Overall Check PQ
ST-001 | DEL-001 | Study Document | Final Study Protocol | Ana Markovic Smith | 2026-08-01 | 2026-08-05 | 2026-08-05 | Completed | High | 0 | PASS | Final approved protocol | Valid | Valid | PASS
ST-001 | DEL-002 | Regulatory | Regulatory Submission Package | Jelena Nikolic | 2026-08-03 | 2026-08-10 |  | Overdue | Critical | 56 | FAIL | Submission package incomplete | Valid | Valid | PASS
ST-001 | DEL-003 | TMF | TMF Filing Package | Marko Petrovic | 2026-08-05 | 2026-08-12 |  | In Progress | High | 54 | PASS | Filing in progress | Valid | Valid | PASS
ST-001 | DEL-004 | Data | Database Review Report | Stefan Ilic | 2026-08-08 | 2026-08-15 | 2026-08-15 | Completed | Medium | 0 | PASS | Database review completed | Valid | Valid | PASS
ST-002 | DEL-005 | Study Document | Monitoring Plan | Ana Markovic Smith | 2026-08-15 | 2026-08-22 |  | Draft | High | 44 | PASS | Awaiting final review | Valid | Valid | PASS
ST-002 | DEL-006 | Site Management | Site Initiation Report | Marko Petrovic | 2026-08-18 | 2026-08-20 | 2026-08-20 | Completed | Medium | 0 | PASS | Site initiation completed | Valid | Valid | PASS
ST-002 | DEL-007 | Data | Data Management Plan | Stefan Ilic | 2026-08-20 | 2026-08-25 |  | In Progress | High | 41 | PASS | Data management review ongoing | Valid | Valid | PASS
ST-002 | DEL-008 | Regulatory | Ethics Committee Submission | Jelena Nikolic | 2026-08-20 | 2026-08-28 |  | Overdue | Critical | 38 | FAIL | Submission delayed | Valid | Valid | PASS